## GANTT
Task | Category | Days From Now | Days To Complete Milestone | Start Date | End Date
Finish Proposal Draft | Proposal | 0 | 4 | 2021-09-27 | 2021-10-01
Finish Final Proposal | Proposal | 11 | 18 | 2021-10-08 | 2021-10-15
Prepare Thesis Proposal Presentation | Proposal | 24 | 32 | 2021-10-21 | 2021-10-29
Clean Reddit Text Data | Data | 18 | 39 | 2021-10-15 | 2021-11-05
Load Stock Data for Securities | Data | 34 | 39 | 2021-10-31 | 2021-11-05
Sentiment Analysis | Algorithm & Evaluation | 39 | 53 | 2021-11-05 | 2021-11-19
Compare Sentiment Analysis Algorithms | Algorithm & Evaluation | 53 | 56 | 2021-11-19 | 2021-11-22
Predict Changes in Stock Prices | Algorithm & Evaluation | 57 | 60 | 2021-11-23 | 2021-11-26
Compare Prediction Algorithms | Algorithm & Evaluation | 60 | 63 | 2021-11-26 | 2021-11-29
Write First Draft of Thesis | Writing | 63 | 87 | 2021-11-29 | 2021-12-23
Finalize Thesis | Writing | 92 | 116 | 2021-12-28 | 2022-01-21
Formulas:
Days From Now = Table1[[#This Row],[Start Date]]-TODAY()
Days From Now = IF(Table1[[#This Row],[Start Date]]-TODAY()>0,Table1[[#This Row],[Start Date]]-TODAY(),0)