## GANTT
Task | Category | Days From Now | Days To Complete Milestone | Start Date | End Date
Finish Proposal Draft | Proposal | 0 | 2 | 2021-09-29 | 2021-10-01
Finish Final Proposal | Proposal | 9 | 2 | 2021-10-08 | 2021-10-10
Prepare Thesis Proposal Presentation | Proposal | 22 | 8 | 2021-10-21 | 2021-10-29
Clean Reddit Text Data | Data | 0 | 6 | 2021-09-29 | 2021-10-05
Load Stock Data for Securities | Data | 0 | 6 | 2021-09-29 | 2021-10-05
Sentiment Analysis | Algorithm & Evaluation | 37 | 7 | 2021-11-05 | 2021-11-12
Compare Sentiment Analysis Algorithms | Algorithm & Evaluation | 20 | 12 | 2021-10-19 | 2021-10-31
Predict Changes in Stock Prices | Algorithm & Evaluation | 32 | 12 | 2021-10-31 | 2021-11-12
Compare Prediction Algorithms | Algorithm & Evaluation | 44 | 12 | 2021-11-12 | 2021-11-24
Write First Draft of Thesis | Writing | 20 | 45 | 2021-10-19 | 2021-12-03
Finalize Thesis | Writing | 90 | 24 | 2021-12-28 | 2022-01-21